## ADP Sample
ADP
Sl. No. | Financial Year | Funding Type | Project Name | Date of Project Approval | Project Start : | Project Ending | Estimated Cost (Lac Tk.) | Package No. & Name | PE Office | Division Office/ | Tender Publication Date | Tender Opening Date | Evaluation Report (ER) Submission Date | Date of Tender Approval by PD/HOPE | Date of ER Submission to Ministry by HOPE | Approval by Minister | Approval by CCGP | Date of Commencement | Contract Value (Lac Tk.) | Name of contractor | Date of Completion | Progress |  | Remarks on Quality of Works
[10 empty] | PM Office | [11 empty] | physical | financial
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 21 |  | 20 | 24 | 22 | 23 | 25
1 | 2017 | GOB | 3rdKarnaphuly Bridge |  |  |  |  | P-1 | Dhaka Zone | Dhaka Division | 2018-01-01 | 2018-01-28 | 2018-02-15 | - | 2018-02-22 | 2018-03-01 | - | 2018-03-30 |  | Kamal Associates | - | 10% | 11% | Satisfactory
[8 empty] | P-2 | Dhaka Circle | Dhaka Division | 2018-01-01 | 2018-01-28 | 2018-02-15 | 2018-02-25 | - | - | - | 2018-03-30 |  | Kamal Associates | - | 10% | 11% | Satisfactory
[8 empty] | P-3 | Dhaka Division | Dhaka Division | 2018-01-01 | 2018-01-28 | 2018-02-15 | [6 empty] | Kamal Associates
[8 empty] | P-4 | Dhaka Zone | Dhaka Division | 2018-01-01 | 2018-01-28 | 2018-02-15 | 2018-02-23 | - | - | - | 2018-03-30 |  | Rana Builders-Navana Construction- JV | - | 10% | 11% | Satisfactory
P-5
2 |  |  | SASEC-1 |  |  |  |  | WP-1 | PD | PM-1 (Joydevpur) | 2018-01-01 | 2018-01-28 | 2018-02-15 | - | 2018-02-22 | - | 2018-03-15 | 2018-03-30 |  | Rana Builders-Navana Construction- JV | - | 10% | 11% | Satisfactory
[8 empty] | WP-2 | PD
3

## PMP Sample
PMP
Sl. No. | Financial Year | Program Type (Major/Minor) | Work Type( Roads/Bridge) | Work description | Date of Program Approval | Estimated Cost (Lac Tk.) | PE Office | Division Office | Tender Publication Date | Tender Opening Date | Evaluation Report (ER) Submission Date | Date of Tender Approval by HOPE | Date of ER Submission to Ministry by HOPE | Approval by Minister | Date of Approval by CCGP | Commence Date | Contract Value (Lac Tk.) | Name of Contractor | Date of Completion | Progress |  | Remarks on Quality of Works
[20 empty] | Physical | Financial
1 | 2018 | Major | Roads | Periodic Maintenance Programme (PMP) providing DBS wearing course at 0+000 to 8+000 km of Bonpara-Gopalpur-Lalpur Road & 0+000 to 7+000 km of Walia-Dayarampur-Sonapur-Shankerbhagerhat-Natore Road under Road Division, Natore during the year 2017-18. |  | 15 | Dhaka Zone | Dhaka Division | 2018-01-01 | 2018-01-28 | 2018-02-15 | - | 2018-02-22 | 2018-03-01 |  | 2018-03-30 | 14.7 |  |  | 15 | 11% | Satisfactory

## Sheet2 (hidden)
Sl. No. | Financial Year | Program Type (Major/Minor) | Work Type( Roads/Bridge) | Work description | Date of Program Approval | Estimated Cost (Lac Tk.) | PE Office | Division Office | Tender Publication Date | Tender Opening Date | Evaluation Report (ER) Submission Date | Date of Tender Approval by HOPE | Date of ER Submission to Ministry by HOPE | Approval by Minister | Date of Approval by CCGP | Commence Date | Contract Value (Lac Tk.) | Name of Contractor | Date of Completion | Progress |  | Remarks on Quality of Works
[20 empty] | Physical | Financial
1 | 2018 | Major | Roads | Periodic Maintenance Programme (PMP) providing DBS wearing course at 0+000 to 8+000 km of Bonpara-Gopalpur-Lalpur Road & 0+000 to 7+000 km of Walia-Dayarampur-Sonapur-Shankerbhagerhat-Natore Road under Road Division, Natore during the year 2017-18. |  | 15 | Dhaka Zone | Dhaka Division | 2018-01-01 | 2018-01-28 | 2018-02-15 | - | 2018-02-22 | 2018-03-01 |  | 2018-03-30 | 14.7 |  |  | 15 | 11% | Satisfactory